SUNDIAL ENGINEERING & SURVEY

4720 South Rainbow Boulevard, Suite 210  ·  Las Vegas, NV 89103  ·  (702) 555-0142  ·  NV COA #C-3874

MEMORANDUM

| TO: | Garrett Nokes, Vice President, Land Development Callaway Land Partners, 8880 W. Sunset Road, Suite 400, Las Vegas, NV 89148 |
| --- | --- |
| FROM: | Max Braddock, Project Manager, Sundial Engineering & Survey |
| CC: | Jonathan R. Kessler, PE, Principal-in-Charge; Project File 2201-03 |
| DATE: | 10/31/2026 |
| RE: | Desert Sage Ranch Phase 3 — Engineer's Estimate, Section 2 (Storm Drain and Detention) checked against the plans; revised bond figure Job No. 2201-03 · IP-26-100288 · FM-26-100290 |

1.  Summary

Before the Phase 3 estimate goes to your surety broker, we checked Section 2 of the Engineer's Estimate of Probable Cost (Rev. 0, 10/10/2026) line by line against Sheets C-6, C-8 and C-9 of the Phase 3 Improvement Plans (first submittal, 08/21/2026) and against the pipe reach schedule in the Phase 3 Storm Drain HGL workbook. Section 2 goes up by $32,505, and the bond figure goes up by $33,000.

|  | Rev. 0 (10/10/2026) | Corrected | Change |
| --- | --- | --- | --- |
| Section 2 subtotal — Storm Drain and Detention | $1,276,934 | $1,309,439 | +$32,505 |
| Construction subtotal, Sections 1–8 | $4,856,565.75 | $4,889,070.75 | +$32,505 |
| Section 9 allowances (agreed lump sums, unchanged) | $500,000 | $500,000 | — |
| Bond figure, rounded up to the next $1,000 (Sched. Sec. 12.02) | $5,357,000 | $5,390,000 | +$33,000 |

Please don't send the $5,357,000 figure to the broker. The bond figure is $5,390,000. We will reissue the estimate as Rev. 1 under Mr. Kessler's seal, and that figure goes to the broker with it. Six items are flagged in Table 2 because the Unit Cost Schedule has nothing that matches what the plans show. Where a flagged item already carries an amount, that amount stays in the subtotal. Resolving them could still move the number.

2.  Basis of the check

Unit prices are from the Clark County Uniform Unit Cost Schedule, effective 01/01/2026, which is the schedule the estimate cites. Where the Schedule says "Actual," the amount already carried stands.

Quantities are taken off the plans. Where the plans give no dimension or stationing for a line already in the estimate, the quantity already carried stands.

Pipe lengths are the reach lengths in the HGL Pipe Schedule. Each one matches the C-8 stationing. They're rounded up to the next whole foot.

Work shown on the plans but missing from the estimate is added at the matching Schedule price.

Where the Schedule has nothing matching what the plans show, the item is flagged, and any amount already carried is left in the subtotal.

Line extensions are to the dollar. Sections 1 and 3 through 9 were not part of this check and are carried unchanged.

3.  Quantity and unit-price changes (Table 1)

| No. | Item | Description | Sheet | Rev. 0 | Corrected | Change |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2.35 → 2.36 | Storm drain manhole: 48-in, ≤ 8 ft → 60-in (5-ft ID), ≤ 10 ft; count per structure schedule | C-8 (Storm Drain Design Notes; Structure Schedule) | 14 EA × $6,400 = $89,600 | 10 EA × $8,750 = $87,500 | −$2,100 |
| 2 | 2.38 (added) | Storm drain manhole, additional depth beyond schedule (over 10 ft) | C-8 (Structure Schedule rims and inverts) | Not carried | 22.02 VF × $685 = $15,084 | +$15,084 |
| 3 | 2.03 (added) | 30-in RCP, Class III, outlet control structure to existing 30-in outfall stub | C-9 (Section A–A′; outlet detail); C-6 (stub invert) | Not carried | 100 LF × $138 = $13,800 | +$13,800 |
| 4 | 3.05 (added in Sec. 2) | Basin access ramp, 6-in aggregate base, 15 ft × 136.7 ft | C-9 (Access Ramp detail); C-6 (basin notes) | Not carried | 227.8 SY × $9.25 = $2,107 | +$2,107 |
| 5 | 3.05 (added in Sec. 2) | Basin maintenance path, top of north berm, 6-in aggregate base, 12 ft × 293 ft | C-9 (Section B–B′); C-6 (basin plan) | Not carried | 390.7 SY × $9.25 = $3,614 | +$3,614 |
|  |  | Net change to Section 2 |  |  |  | +$32,505 |

Notes to Table 1

1.	Manholes. The C-8 Storm Drain Design Notes say "All manholes are 5-foot inside diameter unless noted otherwise." No manhole is noted otherwise, and S-1 is called out as a 5' dia. manhole. Rev. 0 priced 48-inch manholes (Sched. 2.35); the 60-inch item is Sched. 2.36. The C-8 Structure Schedule types ten structures as manholes: S-1, S-2, S-4, S-6, S-7, S-8, S-10, S-11, S-12 and S-14. S-3, S-5, S-9 and S-13 are typed "Curb inlet" only, so they fall under the catch basin line (flagged in Table 2), not the manhole line.

2.	Manhole depth. Sched. 2.36 covers depths to 10 ft. Depth is the C-8 rim elevation minus invert out. Seven manholes are deeper than 10 ft: S-6 10.71 ft (0.71 VF over), S-7 11.29 (1.29), S-8 12.08 (2.08), S-10 13.49 (3.49), S-11 14.03 (4.03), S-12 14.68 (4.68) and S-14 15.74 (5.74), for a total of 22.02 VF. S-1 (7.00 ft), S-2 (7.77 ft) and S-4 (8.95 ft) are within 10 ft.

3.	30-inch outlet pipe. C-9 shows new 30-inch RCP running from the outlet control headwall (invert 2,851.00) to the existing shared outfall stub (invert 2,850.75, per C-6) at 0.25%. Length is 0.25 ft ÷ 0.0025 = 100.0 ft, so 100 LF. Rev. 0 doesn't include this pipe.

4.	Access ramp. On C-9 the ramp is 15 ft wide at 6%, running from top of berm (2,859.20) to basin bottom (2,851.00). That's 8.20 ÷ 0.06 = 136.7 ft long and 2,050 SF, or 227.8 SY. C-6 and C-9 both call for a 6-inch aggregate base surface. Sched. 2.47 (access ramp) is 4-inch AC over 6-inch base, and the plans show no AC. The Schedule item that matches the section shown is 3.05, 6-inch aggregate base course. Ramp subgrade and berm earthwork belong to Section 1 and aren't duplicated here.

5.	Maintenance path. C-9 Section B–B′ shows a 12-ft-wide, 6-inch aggregate base path on top of the north berm. The north berm runs the 293-ft top-of-berm long axis shown on C-6, so 12 × 293 = 3,516 SF, or 390.7 SY, at Sched. 3.05.

4.  Flagged items: the Schedule has nothing matching what the plans show (Table 2)

| Item | What the plans show (sheet) | Closest Schedule items | Left in subtotal |
| --- | --- | --- | --- |
| 2.30 Catch basin, Type A (12 EA carried) | Type G curb inlets with 8-ft opening per SD-305 (C-8 Storm Drain Design Notes). The C-8 Structure Schedule shows 9 curb inlets (S-2, S-3, S-4, S-5, S-6, S-8, S-9, S-12, S-13) at rim-to-invert depths of 7.77 to 15.31 ft. | 2.30/2.31 Type A curb inlet; 2.32 Type B grated; 2.33 combination inlet. No Type G. | $58,200 |
| 2.42 Riprap, D50 = 12 in (500 SY carried) | Spillway apron, 15 × 20 ft of grouted riprap, D50 = 12 in, which is 33.3 SY (C-9). Riprap at the outfall pipe invert per SD-402, not dimensioned (C-6). | 2.42 loose riprap, D50 = 12 in; 2.43 grouted riprap, D50 = 18 in. No grouted D50 = 12 in. | $43,000 |
| 2.99 Field connections to Phase 2 outfall, allowance | Tie of the new 30-in RCP to the existing outfall stub (C-6, C-9). Line B tie to the existing Phase 2 stub at Chuckwalla Way Sta. 3+60 (C-8). | No connection item. RCP prices include connections to structures (Sched. Sec. 2, Note (a)). | $2,300 |
| Not in Rev. 0: spillway weir surface | 12 × 18-in articulated concrete block over geotextile on the 20 × 6-ft weir, 120 SF (C-9). | None. | $0 |
| Not in Rev. 0: basin vehicle gate | 12-ft swing gate, chain-link with privacy slats, at the top of the ramp (C-9). | 10.06 vehicular gate is tubular steel. 2.46 fencing is per LF and excludes gates. | $0 |
| Not in Rev. 0: side-slope topsoil and hydroseed | 12-in topsoil with hydroseed on the basin side slopes (C-9). That's about 28,500 SF of interior slope, based on the C-6/C-9 geometry. | None. | $0 |
|  | Total left in subtotal for flagged items |  | $103,500 |

Each flagged item needs either a Department-accepted alternate unit price under Sched. Sec. 12.04, carried as an "A" item, or a plan revision to a scheduled item. Until then, the bond figure carries $103,500 for the three flagged Rev. 0 lines and nothing for the three items that aren't in Rev. 0.

5.  Corrected Section 2 and bond figure (Table 3)

| Item | Description | Qty | Unit | Unit price | Amount | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 2.03 | 30-in RCP, Class III, in trench (outlet structure to existing outfall stub) | 100 | LF | $138.00 | $13,800 | Added (C-9) |
| 2.04 | 36-in RCP, Class III, in trench (S-1 to S-5) | 870 | LF | $172.00 | $149,640 | Confirmed (C-8 / HGL) |
| 2.06 | 48-in RCP, Class III, in trench (S-5 to S-8) | 687 | LF | $258.00 | $177,246 | Confirmed (C-8 / HGL) |
| 2.08 | 60-in RCP, Class III, in trench (S-8 to S-14 and Line B) | 1,334 | LF | $372.00 | $496,248 | Confirmed (C-8 / HGL) |
| 2.30 | Catch basin, Type A, standard curb inlet, depth ≤ 6 ft | 12 | EA | $4,850.00 | $58,200 | Flagged; carried |
| 2.34 | Drop inlet, area drain | 2 | EA | $3,900.00 | $7,800 | Carried; not dimensioned |
| 2.36 | Storm drain manhole, 60-in dia., depth ≤ 10 ft (replaces 2.35) | 10 | EA | $8,750.00 | $87,500 | Changed (C-8) |
| 2.38 | Storm drain manhole, additional depth beyond schedule | 22.02 | VF | $685.00 | $15,084 | Added (C-8) |
| 2.39 | Junction structure, cast-in-place, sized per plan | 60 | CY | $1,150.00 | $69,000 | Carried; not dimensioned |
| 2.40 | Headwall, cast-in-place, up to 48-in pipe | 2 | EA | $5,400.00 | $10,800 | Carried; not dimensioned |
| 2.42 | Riprap, D50 = 12 in, on filter fabric | 500 | SY | $86.00 | $43,000 | Flagged; carried |
| 2.44 | Detention basin excavation, unclassified (6.4 ac-ft allocation) | 10,000 | CY | $9.75 | $97,500 | Carried; not determinable |
| 2.45 | Detention basin outlet structure, per plan | 1 | LS | $28,000.00 | $28,000 | Schedule "Actual"; stands |
| 2.46 | Detention basin fencing, 6-ft chain link with 3-strand barbed | 1,400 | LF | $34.00 | $47,600 | Carried; not dimensioned |
| 3.05 | Basin access ramp, 6-in aggregate base | 227.8 | SY | $9.25 | $2,107 | Added (C-9) |
| 3.05 | Basin maintenance path, 6-in aggregate base | 390.7 | SY | $9.25 | $3,614 | Added (C-9) |
| 2.99 | Field connections to Phase 2 storm outfall structure and adjustments, allowance | 1 | LS | $2,300.00 | $2,300 | Flagged; carried |
|  | Section 2 subtotal — Storm Drain and Detention |  |  |  | $1,309,439 |  |

| Bond roll-up | Amount |
| --- | --- |
| Section 1 — Earthwork (unchanged) | $504,191.75 |
| Section 2 — Storm Drain and Detention (corrected) | $1,309,439.00 |
| Sections 3 through 8 (unchanged) | $3,075,440.00 |
| Construction subtotal, Sections 1–8 | $4,889,070.75 |
| Section 9 — agreed lump-sum allowances, Addendum No. 1, items 11.05/11.06 (unchanged) | $500,000.00 |
| Total before rounding | $5,389,070.75 |
| Bond figure, rounded up to the next $1,000 (Sched. Sec. 12.02) | $5,390,000 |

Lines confirmed or carried without change

2.04, 2.06 and 2.08 RCP. C-8 station differences match the HGL reaches. 36-inch, S-1 to S-5 (R1–R4): 869.58 LF, so 870. 48-inch, S-5 to S-8 (R5–R7): 686.51 LF, so 687. 60-inch, S-8 to S-14 (R8–R13): 1,093.56 LF, plus Line B to S-15 (R14) at 240.00 LF, totals 1,333.56 LF, so 1,334. Unit prices match Sched. 2.04, 2.06 and 2.08. C-6 gives no dimension or stationing for Line B, so the 240-LF length the HGL scaled from C-6 is carried.

2.34 drop inlets, 2.39 junction structure, 2.46 basin fencing. C-6, C-8 and C-9 don't locate or dimension any drop inlet, cast-in-place junction structure or basin fence line, so the carried quantities stand. C-8 junction manholes are precast per SD-301, and C-9 lists the basin appurtenances as outlet control, spillway, access ramp, gate and maintenance path. For reference, the top-of-berm perimeter is about 976 LF, against 1,400 LF of fence carried.

2.40 headwalls. The plans don't schedule any headwall apart from the outlet control headwall, which is part of 2.45. S-1 (headwall/cleanout) is on 36-inch pipe, which is within the up-to-48-inch item. The carried quantity stands.

2.44 basin excavation. Cut volume depends on existing grade at the basin, and C-6 and C-9 don't give it. The carried quantity stands. For reference, the C-9 storage table gives 6.40 ac-ft (about 10,330 CY) to the 100-year water surface and 8.02 ac-ft (about 12,940 CY) to top of berm.

2.45 outlet structure. The Schedule price is "Actual, ≥ $18,000," so the $28,000 carried stands. It covers the headwall, orifice plate and trash rack detailed on C-9.

Not added because it's Section 1 work: berm and spillway fill, ramp subgrade, and the 6-inch compacted native soil at basin bottom (rough grading of drainage tracts, Sched. 1.14).

6.  What could still move Section 2

The flagged items in Table 2.

This check is against the 08/21/2026 first-submittal sheets. The County's drainage comments (G-3 through G-7) and the north-boundary easement comments (U-1, U-5, A-1) may change Section 2 at resubmittal. As drawn, Line A runs 10 ft south of the north boundary, inside the 20-ft dry utility easement recorded on the Phase 1–2 map.

Line B. S-14 sits at the northeast corner of the parcel (CP-118), and the basin is in the southwest quadrant (C-6). The 240 LF carried for Line B needs to be confirmed on the resubmittal drawings. Each added foot of 60-inch RCP is $372.

S-15. The basin inflow structure on the 60-inch Line B is referenced on C-8 but not typed or detailed on C-6. If it's a headwall, Sched. 2.41 ($8,200 each) applies.

We'll rerun Section 2 against the resubmittal set before the bond is posted.

______________________________

Max Braddock

Project Manager, Sundial Engineering & Survey

mbraddock@sundialensv.com  ·  (702) 555-0144