## Cover
Fill Placement and Grading Records - Block A Slab-on-Grade
Rowan Bay Constructors, Inc. - Field Engineering
4400 Alum Creek Drive, Columbus, OH 43207 - (614) 555-0192
Record No.: RB-FPR-BA-2026
Record Period: 06/22/2026 - 07/08/2026
Field | Entry
Project | Birchwood Village Expansion Program - Package A
Site | 1802 Larchwood Avenue, Columbus, OH 43210
Owner | Thornbury State University
Contractor | Rowan Bay Constructors, Inc.
Area of work | Block A slab-on-grade fill pad (structural fill beneath slab-on-grade)
Superintendent | Marcus Whitfield
Field engineer of record (Contractor) | E. Halstrom, Rowan Bay Field Engineering
Record type | Daily fill placement and grading log - Block A slab-on-grade structural fill
Placement start | 06/22/2026
Placement complete | 07/08/2026
Elevation range | From proof-rolled subgrade El. 745.0 to finished fill grade El. 748.6
Total thickness | 3.6 ft
Number of lifts | 6 lifts
Nominal lift thickness | 8 in loose; ~7.2 in compacted
Plan area of pad | 11,400 sf (Block A slab-on-grade footprint, grids B-G / 1-5)
Borrow source | Stockpile north of Block C - approved for reuse per RFI 079
Governing Proctor reference | Vantree Materials Testing Report VMT-25-0918-P04, ASTM D1557 Method C, γd,max = 128.4 pcf, wopt = 9.2%
Compaction acceptance basis | Specification Section 31 20 00, Article 3.4.B
Subgrade preparation | Topsoil and existing uncontrolled fill stripped to El. 745.0; subgrade proof-rolled 06/18/2026 with loaded tandem-axle dump truck in the presence of Vantree Materials Testing; written acceptance issued by Thelbridge Project Management Services, memo TPM-26-063 dated 06/18/2026
Production test strip | Executed 06/19/2026 at the north end of the pad, witnessed by Vantree Materials Testing and Thelbridge Project Management Services; established 6 coverage passes of the CS56B smooth-drum with pneumatic follow-pass at 8 in loose lift thickness for production placement
Working grade / next operation | El. 748.6, capillary break and slab-on-grade construction
Compaction equipment | Caterpillar CS56B smooth-drum vibratory roller (primary) with Caterpillar PS-150C pneumatic-tire roller on follow-pass; Wacker DPU 6555 walk-behind plate at edges and tie-ins
Field density testing | ASTM D6938 nuclear gauge, performed by Vantree Materials Testing (Owner's testing lab)
Cross-reference - density reports | Lifts 1 through 5 covered by Vantree field density reports FDR-BA-01 through FDR-BA-05, issued lift-by-lift, three tests per lift. Lift 6 covered by Field Density Report SF-26-0708, tests FD-14 through FD-17
Working shift | 0700 to 1700, Monday through Friday. Placement, grading and compaction ran the full shift on each lift date.

## Daily Placement Log
Daily Placement Log - Block A Slab-on-Grade Structural Fill
Column Key
Lift | Sequential lift number, bottom-up.
Date | Date of lift placement and compaction.
Working El. (top of lift, ft) | Nominal top-of-compacted-lift elevation.
Loose thk (in) | Average loose lift thickness spread by dozer prior to compaction.
Compacted thk (in) | Average measured lift thickness after acceptance-pass compaction.
Area covered (sf) | Plan area of the Block A slab-on-grade pad filled that day.
Loads | Number of loaded haul-unit trips received from the source stockpile (nominal 14 CY per unit).
Weather | General daytime conditions on site.
Passes - smooth drum | Number of coverage passes with the CS56B vibratory smooth drum.
Passes - pneumatic / plate | Coverage passes with the PS-150C pneumatic follow-pass roller and, at edges and tie-ins, the walk-behind plate.
Operator initials | Roller operator on shift (RB employee).
Density tests taken | Field density test identifiers taken by Vantree during or immediately after lift completion.
Remarks | Field notes.
Lift | Date | Working El. (ft) | Loose thk (in) | Compacted thk (in) | Area covered (sf) | Loads | Weather | Passes - smooth drum | Passes - pneumatic / plate | Operator initials | Density tests taken | Remarks
1 | 06/22/2026 | 745.6 | 8 | 7.2 | 11400 | 23 | Clear, 68-84 F, calm | 6 | 4 | J.T.M. | FDR-BA-01 (3 tests) | Placement commenced on the proof-rolled subgrade at El. 745.0. Grade-control stakes checked by field eng. E.H. Haul from the source stockpile staged through the Block C access road.
2 | 06/23/2026 | 746.2 | 8 | 7.2 | 11400 | 22 | Partly cloudy, 66-81 F, breezy | 6 | 4 | J.T.M. | FDR-BA-02 (3 tests) | Routine placement. Water truck used on the east half to bring surface moisture up before rolling.
3 | 06/25/2026 | 746.8 | 8 | 7.2 | 11400 | 23 | Clear, 70-88 F, calm | 6 | 4 | R.K.S. | FDR-BA-03 (3 tests) | No placement 06/24; crew on site utilities. Surface scarified 2 in AM prior to next-lift bond.
4 | 06/26/2026 | 747.4 | 8 | 7.2 | 11400 | 23 | Clear, 72-90 F, calm | 6 | 4 | R.K.S. | FDR-BA-04 (3 tests) | Routine placement. Stockpile face reworked by dozer at 1300 to keep feed uniform.
5 | 06/30/2026 | 748 | 8 | 7.2 | 11400 | 22 | Hot, 74-93 F, calm | 7 | 4 | M.S.B. | FDR-BA-05 (3 tests) | No fill placement 06/27 to 06/29 (weekend, then crew supporting basement work Monday). One rework pass covering approximately 1,500 sf near grid E-4 for moisture correction on the dry side; water applied and re-rolled.
6 | 07/08/2026 | 748.6 | 8 | 7.2 | 11400 | 23 | Clear, 71-84 F, calm | 6 | 4 | M.S.B. | FD-14 to FD-17 (4 tests, Report SF-26-0708) | No placement 07/01 to 07/07 (crew on basement support; 07/03 holiday). Pad surface re-checked and lightly bladed before the final lift. Final lift completed to fill grade El. 748.6, graded to +/- 0.1 ft. Vantree on site 0715-1130 for in-lift density testing. Pad left ready for the capillary break course.
Totals (Block A slab-on-grade fill, 06/22/2026 - 07/08/2026)
Total lifts placed |  | 6 lifts
Nominal thickness placed |  | 3.6 ft (El. 745.0 to El. 748.6)
Plan area of pad |  | 11,400 sf
Total haul units received |  | 136 units (nominal 14 CY/unit, approx. 1,904 CY loose; approx. 1,520 CY compacted in place)
Total field density tests taken |  | 19 (15 in Lifts 1-5 under reports FDR-BA-01 to FDR-BA-05; 4 in Lift 6 under Report SF-26-0708)
Working shifts worked |  | 6

## Notes
Notes
No. | Note
1 | Fill placed on the stripped and proof-rolled subgrade at El. 745.0 within the Block A slab-on-grade footprint, grids B-G / 1-5. Plan area of the pad is 11,400 sf. Each lift covered the full pad area.
2 | Subgrade proof roll performed 06/18/2026 with a loaded tandem-axle dump truck in the presence of Vantree Materials Testing. Written acceptance of the subgrade was issued by Thelbridge Project Management Services under memo TPM-26-063 dated 06/18/2026 prior to the first lift.
3 | Production test strip executed 06/19/2026 at the north end of the pad, witnessed by Vantree Materials Testing and Thelbridge Project Management Services. The strip established 6 coverage passes of the CS56B smooth-drum vibratory roller with pneumatic follow-pass at 8 in loose lift thickness as the production pattern.
4 | Structural fill for this pad was drawn from the stockpile north of Block C, approved for reuse under RFI 079 (closed 10/10/2025). Haul was by on-site scraper and articulated truck from the stockpile face; no off-site delivery tickets apply to this work.
5 | Governing laboratory Proctor carried on this record is Vantree Materials Testing Report VMT-25-0918-P04 dated 09/18/2025, ASTM D1557 Method C, γd,max = 128.4 pcf, wopt = 9.2%, as used on the Block B mass fill record RB-FPR-BB-2025.
6 | Lift acceptance: each lift was tested by Vantree Materials Testing before the succeeding lift was placed, in accordance with Specification Section 31 20 00 Article 1.6.B. Field density reports were issued lift-by-lift as FDR-BA-01 through FDR-BA-05, three tests per lift; Lift 6 results are reported in Field Density Report SF-26-0708.
7 | Weather: no full shifts lost. Ambient temperatures ran high through the placement period and surface moisture loss between spreading and rolling was noted by the field engineer on 06/26 and 06/30.
8 | Retest and rework: interim rework passes for moisture correction and additional roller coverage are noted in the Remarks column and are covered in more detail in the daily field density reports.
9 | Distribution: original filed with Rowan Bay field engineering; copy transmitted to Thelbridge Project Management Services (Owner's Representative) and to Vantree Materials Testing for correlation with the field density reports.

## Signature
Signature
Records prepared and certified true and complete by:
Signature: | /s/ Marcus Whitfield, Superintendent
Name | Marcus Whitfield
Title | Superintendent
Company | Rowan Bay Constructors, Inc.
Field trailer | (614) 555-0192 x811
Email | mwhitfield@rowanbay.com
Date of signature | 07/09/2026